Scope of Work
1530 3rd St NE
Rochester, MN  55906
6/29/2026 – RFP Scope

Lead Paint Assessment was Clear

Exterior 
Front Step 
· Remove wood steps and replace with precast or freestanding wood/trex composite
Painting
· None planned
Gutters
· Install 5” gutters and large downspouts - white
Concrete
· No work planned at this time


Interior
Painting
· Possibly painting new closet shelves/base shoe/cabinet duct box if needed
Flooring
· No work
Carpentry
· Box around new range hood duct above cabinet
· Add rod and shelf to 2 bedroom closets @ 60” AFF
· Add shelves to pantry closet
· Add shelves and a door to hall linen closet
· Add base shoe to kitchen cabinets
Plumbing
· Install hybrid heat pump style water heater sized for 3-4 people
Electrical
· Hard wire new water heater
HVAC
· Vent range hood to exterior / thru roof
· Add 1 baseboard return air in hallway with 7” duct back to Return Main Duct
· HVAC advise on perm dehumidifier and better balanced return and supply
· Run static pressure test
· Duct cleaning
Radon Mitigation
· not required (2.2)
Insulation
· Spray foam rim joists and seal up penetrations
· Seal off old water heater vent by glass block 
· Attic insulation ok as is
· Air seal around any attic / ceiling penetrations

Provide Option Price for One Car Detached Garage:
12ft wide x 24ft deep on thickened edge slab 
Connect to existing black top driveway
Electrical
Overhead door with electric opener
Interior and exterior lights
Steel side door with dead bolt hardware 

Final Clean can be provided by First Homes










First Homes Action Items
To do
· Change furnace filter
· Clean ERV filter
· Liebenow foundation evaluation
· Install dehumidifier
· Lead assessment
· Test side door water proofing
· Sewer line camera inspection
· Jetter clean sewer line root intrusion
· Energy Audit
Level dryer
Replace duct with rigid good duct
Clean basement floors – sweep, hepa vac, mop
Tape R/A vents
Monitor side door leaks in basement – none so far 6/30

Weird soil smell and high PM2.5 levels
-evaluate after water heater and gutters

FH directed work
Block Foundation
· FH will work with Liebenow Waterproofing to repair foundation
· Tuckpoint larger cracks
Landscaping by FH
· Add seed/straw on bare spots
· Completed 6/19/26
Trees – Work Provided by Others working directly with FH
· Dead Pine Tree in front yard to be removed
· Completed 6/1/26

